## Sheet1
1 | Provide secure sign-up and login functionality | 5 | 1 | 1 | General Requirement
10 | Log In / Sign Up Screen With Text Fields and Submit Button | 3 | 1 | 1
20 | Create a database for storing users, events, teams, and matches | 8 | 1 | 1
23 | Authentication and Registration of Users | 3 | 4 | 1
2 | Support account personalization during sign-up and in settings including team affiliation, locations, and other preferences. | 13 | 2 | 2 | Frontend Requirement
3 | Enable event discovery through search allowing filtering by location, team, data/time, event type, etc. | 3 | 3 | 2 | Backend Requirement
4 | Allow event hosting and management with options to publish event postings with info like location, event type, time and capacity. | 5 | 4 | 2
11 | Account Personlisation Screen with Text Fieds and Pickers | 8 | 2 | 2
12 | Event List Views of all things happening | 8 | 3 | 2
13 | Search Box and Filter Pickers for event trimming | 8 | 4 | 2
14 | Create / Edit Event User Interface | 8 | 5 | 2
21 | Develop RESTful endpoints to search and filter events by multiple criteria: location, team, date/time, and event type | 5 | 2 | 2
22 | Implement CRUD APIs for creating, updating, publishing, and deleting events. | 5 | 3 | 2
5 | Include event registration (RSVP) for users wanting to mark attendance for posted events. | 3 | 5 | 3
6 | Display tournament information like fixtures, scores, lineups, and match statistics. | 8 | 6 | 3
7 | Deliver news feed to users including breaking news, hot topics, team news and general tournament coverage. | 13 | 7 | 3
15 | List of Saved (RSVP) Events | 5 | 5 | 3
16 | Summary of tournament information in a list view user interface | 5 | 6 | 3
17 | News and updates user interface | 5 | 7 | 3
24 | APIs to fetch and categorize news articles, including filtering by topic, team, or event relevance. | 3 | 5 | 3
8 | Include community interaction features like comments on events and host/event reviews | 5 | 9 | 4
9 | Ensure app quality with thorough monitoring, testing, and verification of feature functionality. | 8 | 10 | 4
18 | Comments + Reviews View for Events | 8 | 9 | 4
19 | Polsih User Interface and Experience | 3 | 10 | 4
Requirement ID | Description of Requirement | Story Points | Priority | Sprint No. | Requirement Legend